## Summary
Payments Data Migration: QA Summary
Synthetic data adapted from public PaySim. Fictional bank and roles. Results come from scripts in /python.
Test cases | 30
Latest result: Pass | 27
Latest result: Fail | 0
Latest result: Not Run (UAT) | 3
Defects raised | 10
Defects Critical | 2
Defects High | 6
Defects Medium | 2
Defects Closed | 10
Requirements | 14
Requirements Pass | 11
Requirements Pending UAT | 3
Exceptions, trial load 1 | 4010
Exceptions, rehearsal 2 | 0

## Test Cases
Synthetic data adapted from public PaySim. Fictional bank and roles. Results come from scripts in /python.
ID | Type | Title | Requirement | Method | Expected | Run 1 (trial load 1) | Run 1 evidence | Run 2 (rehearsal 2) | Run 2 evidence | Defect | Latest result
TC-01 | SIT | Record completeness: every legacy payment exists in target | REQ-001 | Run sql/02_reconciliation_rules.sql, rule R01 | 0 exceptions | Fail | 400 exceptions | Pass | 0 exceptions | DEF-001 | Pass
TC-02 | SIT | No target payment exists without a legacy source | REQ-003 | Run sql/02_reconciliation_rules.sql, rule R02 | 0 exceptions | Fail | 200 exceptions | Pass | 0 exceptions | DEF-002 | Pass
TC-03 | SIT | No payment_id appears more than once in target | REQ-002 | Run sql/02_reconciliation_rules.sql, rule R03 | 0 exceptions | Fail | 300 exceptions | Pass | 0 exceptions | DEF-003 | Pass
TC-04 | SIT | Amount matches legacy to the cent | REQ-004 | Run sql/02_reconciliation_rules.sql, rule R04 | 0 exceptions | Fail | 800 exceptions | Pass | 0 exceptions | DEF-004 | Pass
TC-05 | SIT | Originator account migrates at full length | REQ-005 | Run sql/02_reconciliation_rules.sql, rule R05 | 0 exceptions | Fail | 500 exceptions | Pass | 0 exceptions | DEF-005 | Pass
TC-06 | SIT | Settlement date is ISO 8601 (YYYY-MM-DD) | REQ-006 | Run sql/02_reconciliation_rules.sql, rule R06 | 0 exceptions | Fail | 600 exceptions | Pass | 0 exceptions | DEF-006 | Pass
TC-07 | SIT | Settlement date value equals legacy date | REQ-006 | Run sql/02_reconciliation_rules.sql, rule R07 | 0 exceptions | Fail | 300 exceptions | Pass | 0 exceptions | DEF-007 | Pass
TC-08 | SIT | Routing numbers present and 9 digits | REQ-007 | Run sql/02_reconciliation_rules.sql, rule R08 | 0 exceptions | Fail | 500 exceptions | Pass | 0 exceptions | DEF-008 | Pass
TC-09 | SIT | Status codes map STL/PND/RTN to SETTLED/PENDING/RETURNED | REQ-008 | Run sql/02_reconciliation_rules.sql, rule R09 | 0 exceptions | Fail | 400 exceptions | Pass | 0 exceptions | DEF-009 | Pass
TC-10 | SIT | Fraud flag preserved | REQ-009 | Run sql/02_reconciliation_rules.sql, rule R10 | 0 exceptions | Fail | 10 exceptions | Pass | 0 exceptions | DEF-010 | Pass
TC-11 | SIT | Payment method maps W/A to WIRE/ACH | REQ-010 | Run sql/02_reconciliation_rules.sql, rule R11 | 0 exceptions | Pass | 0 exceptions | Pass | 0 exceptions |  | Pass
TC-12 | SIT | Payment direction maps C/D to CREDIT/DEBIT | REQ-010 | Run sql/02_reconciliation_rules.sql, rule R12 | 0 exceptions | Pass | 0 exceptions | Pass | 0 exceptions |  | Pass
TC-13 | SIT | Originator routing value unchanged | REQ-007 | Run sql/02_reconciliation_rules.sql, rule R13 | 0 exceptions | Pass | 0 exceptions | Pass | 0 exceptions |  | Pass
TC-14 | SIT | Beneficiary routing value unchanged | REQ-007 | Run sql/02_reconciliation_rules.sql, rule R14 | 0 exceptions | Pass | 0 exceptions | Pass | 0 exceptions |  | Pass
TC-15 | SIT | Beneficiary account unchanged | REQ-005 | Run sql/02_reconciliation_rules.sql, rule R15 | 0 exceptions | Pass | 0 exceptions | Pass | 0 exceptions |  | Pass
TC-16 | SIT | Trace ID unchanged | REQ-011 | Run sql/02_reconciliation_rules.sql, rule R16 | 0 exceptions | Pass | 0 exceptions | Pass | 0 exceptions |  | Pass
TC-17 | SIT | Routing numbers pass ABA checksum | REQ-007 | Run sql/02_reconciliation_rules.sql, rule R17 | 0 exceptions | Pass | 0 exceptions | Pass | 0 exceptions |  | Pass
TC-18 | SIT | API accepts a valid payment (201) | REQ-013 | Submit api/payloads/TC-18_valid_payment.json to reference validator | HTTP 201 | Pass | HTTP 201 | N/A | No change since run 1 |  | Pass
TC-19 | SIT | API rejects invalid routing checksum (422) | REQ-013 | Submit api/payloads/TC-19_invalid_routing_checksum.json to reference validator | HTTP 422 ERR_ROUTING_INVALID | Pass | HTTP 422 ERR_ROUTING_INVALID | N/A | No change since run 1 |  | Pass
TC-20 | SIT | API rejects missing required field (400) | REQ-013 | Submit api/payloads/TC-20_missing_amount.json to reference validator | HTTP 400 ERR_MISSING_FIELD | Pass | HTTP 400 ERR_MISSING_FIELD | N/A | No change since run 1 |  | Pass
TC-21 | SIT | API rejects negative amount (422) | REQ-013 | Submit api/payloads/TC-21_negative_amount.json to reference validator | HTTP 422 ERR_AMOUNT_INVALID | Pass | HTTP 422 ERR_AMOUNT_INVALID | N/A | No change since run 1 |  | Pass
TC-22 | SIT | API rejects duplicate Idempotency-Key (409) | REQ-013 | Submit api/payloads/TC-22_duplicate_idempotency_key.json to reference validator | HTTP 409 ERR_DUPLICATE_PAYMENT | Pass | HTTP 409 ERR_DUPLICATE_PAYMENT | N/A | No change since run 1 |  | Pass
TC-23 | SIT | API rejects wrong date format (400) | REQ-013 | Submit api/payloads/TC-23_date_wrong_format.json to reference validator | HTTP 400 ERR_DATE_FORMAT | Pass | HTTP 400 ERR_DATE_FORMAT | N/A | No change since run 1 |  | Pass
TC-24 | SIT | API rejects unsupported payment method (400) | REQ-013 | Submit api/payloads/TC-24_unsupported_method.json to reference validator | HTTP 400 ERR_METHOD_UNSUPPORTED | Pass | HTTP 400 ERR_METHOD_UNSUPPORTED | N/A | No change since run 1 |  | Pass
TC-25 | SIT | Control totals tie out (row count, distinct keys, amount total) | REQ-014 | Run sql/03_control_totals.sql | Counts and amount total equal legacy | Fail | Rows 100,100 vs 100,000; amount variance -$4,452,155.93 | Pass | Rows 100,000; amount variance $0.00 | DEF-001, DEF-002, DEF-003, DEF-004 | Pass
TC-26 | Regression | Clean fields stay clean after fixes (R11 to R17) | REQ-014 | Rerun R11 to R17 on rehearsal 2 | 0 exceptions | N/A | Baseline: 0 exceptions on trial load 1 for R11 to R17 | Pass | R11 to R17: 0 exceptions |  | Pass
TC-27 | SIT | Exception log has required columns and one row per exception | REQ-012 | Check data/results/trial1/exceptions.csv columns and row count vs summary | 6 columns, rows equal summary total | Pass | 4,010 rows, columns OK | N/A | No exceptions to log on rehearsal 2 |  | Pass
TC-28 | UAT | Payments Operations reviews the ranked exception report | REQ-012 | Business user reviews exceptions by severity and confirms it is usable | Report accepted | Not Run | Awaiting business users | Not Run | Awaiting business users |  | Not Run
TC-29 | UAT | Compliance confirms all flagged payments retained | REQ-009 | Compliance spot-checks fraud-flagged payments in target | All 122 flagged payments retained | Not Run | Awaiting business users | Not Run | Awaiting business users |  | Not Run
TC-30 | UAT | Finance Controller signs off control totals | REQ-014 | Finance reviews control totals and sign-off sheet | Signed | Not Run | Awaiting business users | Not Run | Awaiting business users |  | Not Run

## Defect Log
Synthetic data adapted from public PaySim. Fictional bank and roles. Results come from scripts in /python. Root causes are simulated hypotheses: the defects were seeded.
ID | Title | Severity | Recon rule | Test case | Records affected | Value of affected payments (USD) | Suspected root cause (simulated) | Fix | Found in | Status | Retest
DEF-001 | Payments missing from target | Critical | R01 | TC-01 | 400 | 103846573.27 | Load job skipped rows that failed a target constraint without logging them | Log and reject every skipped row. Add completeness check before cutover. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-002 | Records in target with no legacy source | High | R02 | TC-02 | 200 | 46804254.68 | Rows from an earlier test load were not purged before the trial load | Purge target before each load. Add R02 as a pre-cutover gate. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-003 | Duplicate payment_id in target | High | R03 | TC-03 | 300 | 52590152.38 | Load job restarted mid-batch and re-inserted rows, no unique key enforced | Enforce unique key on payment_id. Make load restartable. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-004 | Amounts rounded to whole dollars (absolute error $201.46 in total) | High | R04 | TC-04 | 800 | 144571998 | One ETL path cast amounts to integer | Use Decimal(18,2) end to end. Remove integer cast. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-005 | Originator account numbers truncated | Medium | R05 | TC-05 | 500 | 79638298.68 | Target column defined too narrow (see FG-04) | Widen column to at least 11 characters (CR-004). | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-006 | Settlement date written as MM/DD/YYYY | Medium | R06 | TC-06 | 600 | 102000761.4 | Second code path used a different date format | Single ISO 8601 conversion function for all paths. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-007 | Settlement date shifted by one day | High | R07 | TC-07 | 300 | 52861403.3 | Timezone conversion moved some dates | Convert dates without timezone logic. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-008 | Beneficiary routing number blank | High | R08 | TC-08 | 500 | 73100733.25 | Blank source field mapped without a required-field check | Reject blanks before load. Add R08 and R17 as gates. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-009 | Pending payments shown as settled | High | R09 | TC-09 | 400 | 72793879.68 | Unmapped PND code defaulted to SETTLED | Explicit lookup, reject unmapped codes. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)
DEF-010 | Fraud flag lost on conversion | Critical | R10 | TC-10 | 10 | 25818752.09 | Boolean mapping dropped Y on a subset of rows | Explicit Y to 1 mapping. Keep R10 as a Critical gate. | Trial load 1 | Closed | Retest passed on rehearsal 2 (0 exceptions)

## RTM
Synthetic data adapted from public PaySim. Fictional bank and roles. Results come from scripts in /python.
Requirement | Description | Priority | Test cases | Defects (trial load 1) | Test cases | Latest Pass | Latest Fail | Status
REQ-001 | Every in-scope legacy payment shall exist in the target | Must | TC-01 | DEF-001 | 1 | 1 | 0 | Pass
REQ-002 | No payment_id shall appear more than once in the target | Must | TC-03 | DEF-003 | 1 | 1 | 0 | Pass
REQ-003 | No target payment shall exist without a legacy source | Must | TC-02 | DEF-002 | 1 | 1 | 0 | Pass
REQ-004 | Amount shall match the legacy value to the cent, no rounding | Must | TC-04 | DEF-004 | 1 | 1 | 0 | Pass
REQ-005 | Account numbers shall migrate at full length | Must | TC-05, TC-15 | DEF-005 | 2 | 2 | 0 | Pass
REQ-006 | Settlement date converts to ISO 8601 with the same date value | Must | TC-06, TC-07 | DEF-006, DEF-007 | 2 | 2 | 0 | Pass
REQ-007 | Routing numbers present, 9 digits, ABA checksum valid, unchanged | Must | TC-08, TC-13, TC-14, TC-17 | DEF-008 | 4 | 4 | 0 | Pass
REQ-008 | Status codes map STL, PND, RTN with no defaulting | Must | TC-09 | DEF-009 | 1 | 1 | 0 | Pass
REQ-009 | Fraud flag preserved for every payment | Must | TC-10, TC-29 | DEF-010 | 2 | 1 | 0 | Pending UAT
REQ-010 | Payment method and direction map correctly | Must | TC-11, TC-12 |  | 2 | 2 | 0 | Pass
REQ-011 | Trace ID preserved unchanged | Must | TC-16 |  | 1 | 1 | 0 | Pass
REQ-012 | Every exception logged with rule, severity, legacy and target values | Must | TC-27, TC-28 |  | 2 | 1 | 0 | Pending UAT
REQ-013 | Payment API accepts JSON, validates, returns structured errors | Should | TC-18, TC-19, TC-20, TC-21, TC-22, TC-23, TC-24 |  | 7 | 7 | 0 | Pass
REQ-014 | Go-live needs zero open Critical and High exceptions and signed UAT | Must | TC-25, TC-26, TC-30 |  | 3 | 2 | 0 | Pending UAT

## Change Log
Synthetic data adapted from public PaySim. Fictional bank and roles. Results come from scripts in /python.
ID | Date | Change | Reason | Impact | Requested by | Approver (fictional role) | Status
CR-001 | 2026-10-07 | Add ABA checksum rule R17 to reconciliation | API enforces ABA checksum, so reconciliation must check it too (FG-05) | REQ-007, TC-17 | BA | Core Platform Product Owner | Implemented
CR-002 | 2026-10-07 | Add control rules R11 to R17 for clean fields | Prove fields that should not change did not change | REQ-005, 007, 010, 011, TC-11 to TC-17, TC-26 | BA | QA Lead | Implemented
CR-003 | 2026-10-07 | Classify missing records and fraud flag loss as Critical | Both are irreversible if missed at cutover | REQ-001, REQ-009, severity model | BA | Financial Crime and Compliance | Approved
CR-004 | 2026-10-07 | Widen target account number columns to 11 or more characters | Legacy accounts run to 11 characters (FG-04, DEF-005) | REQ-005, TC-05 | Data Migration Lead | Core Platform Product Owner | Implemented in rehearsal 2
CR-005 | 2026-10-07 | Require Idempotency-Key header on payment API | Prevent duplicate payment submission (TC-22) | REQ-013, TC-22 | BA | Core Platform Product Owner | Implemented in spec v1.0

## RAID Log
Synthetic data adapted from public PaySim. Fictional bank and roles. Results come from scripts in /python.
Type | ID | Description | Impact / detail | Owner (fictional role) | Next step | Status
Risk | RK-01 | Offsetting errors hide in totals: net variance looks small while gross error is large | High impact. Net variance $-4,452,155.93 vs $203,240,980 of missing, duplicate and orphan payments | Finance Controller | Reconcile every payment (R01 to R17), not just totals | Mitigated
Risk | RK-02 | Fraud flag dropped during conversion | Critical. 10 flagged payments lost the flag in trial load 1, $25,818,752 affected | Financial Crime and Compliance | R10 is a Critical gate. Compliance spot-check in UAT (TC-29) | Open, pending UAT
Risk | RK-03 | Pending payments reported as settled | High. 400 of 5,038 pending payments affected in trial load 1 | Payments Operations | Explicit status lookup, R09 gate | Mitigated
Risk | RK-04 | Business users not available for UAT | Medium. Go-live depends on TC-28 to TC-30 | Program Manager | Book UAT slots before rehearsal 3 | Open
Risk | RK-05 | Synthetic data may not reflect real production data quality | Medium. Portfolio project, not a real conversion | BA | State this in the README and on the resume | Accepted
Assumption | AS-01 | Legacy extract is complete and frozen at extract time |  | Data Migration Lead | Confirm extract control total with legacy team | Open
Assumption | AS-02 | Synthetic routing numbers use prefix 99 so they cannot match a real bank |  | BA | None needed | Closed
Assumption | AS-03 | Business rules in the mapping document are approved by the business owner |  | Head of Payments Operations | Walk through mapping in review session | Open
Issue | IS-01 | Trial load 1 produced 4,010 exceptions (4.01% of records) | 400 missing, 300 duplicate, 200 orphan, 10 fraud flags lost, and 6 other types | Data Migration Lead | Fix 10 defects, rerun as rehearsal 2 | Closed (rehearsal 2: 0 exceptions)
Issue | IS-02 | Net control total variance would pass a net-only tolerance check | $4,452,155.93 net vs $203,240,980 gross | Finance Controller | Adopt decision DC-01 | Closed
Decision | DC-01 | Reconcile at payment level as well as in total |  | Head of Payments Operations | Done: rules R01 to R17 | Approved
Decision | DC-02 | How to treat merchant (M-prefix) beneficiary accounts | 33,815 records have M-prefix beneficiaries (FG-12) | Head of Payments Operations | Business owner to decide: add beneficiary type attribute or keep as is | Open
Decision | DC-03 | Severity model: Critical, High, Medium |  | QA Lead | Done: defined in BRD section 7 | Approved
Dependency | DP-01 | Platform team widens account number column (FG-04, CR-004) | Blocks DEF-005 retest | Core Platform Product Owner | Applied in rehearsal 2 | Done
Dependency | DP-02 | Compliance availability for TC-29 | Blocks REQ-009 sign-off | Financial Crime and Compliance | Schedule review | Open
Dependency | DP-03 | Business owner approval of mapping rules | Blocks AS-03 | Head of Payments Operations | Schedule review | Open
Action | AC-01 | Run UAT with Payments Operations (TC-28) |  | Program Manager | Book session | Open
Action | AC-02 | Get decision on merchant account handling (DC-02) |  | BA | Raise at next steering review | Open
Action | AC-03 | Compliance spot-check of 122 fraud-flagged payments (TC-29) |  | Financial Crime and Compliance | Schedule review | Open

## Recon Results
Synthetic data adapted from public PaySim. Fictional bank and roles. Results come from scripts in /python.
Rule | Name | Severity | Exceptions, trial load 1 | Exceptions, rehearsal 2 | Value of affected payments, trial load 1 (USD)
R01 | MISSING_IN_TARGET | Critical | 400 | 0 | 103846573.27
R02 | ORPHAN_IN_TARGET | High | 200 | 0 | 46804254.68
R03 | DUPLICATE_ID | High | 300 | 0 | 52590152.38
R04 | AMOUNT_MISMATCH | High | 800 | 0 | 144571998
R05 | ORIG_ACCOUNT_MISMATCH | Medium | 500 | 0 | 79638298.68
R06 | DATE_NOT_ISO | Medium | 600 | 0 | 102000761.4
R07 | DATE_VALUE_MISMATCH | High | 300 | 0 | 52861403.3
R08 | ROUTING_MISSING_OR_INVALID | High | 500 | 0 | 73100733.25
R09 | STATUS_MISMATCH | High | 400 | 0 | 72793879.68
R10 | FRAUD_FLAG_MISMATCH | Critical | 10 | 0 | 25818752.09
R11 | PAYMENT_METHOD_MISMATCH | High | 0 | 0 | 0
R12 | DIRECTION_MISMATCH | High | 0 | 0 | 0
R13 | ORIG_ROUTING_VALUE_MISMATCH | High | 0 | 0 | 0
R14 | BENE_ROUTING_VALUE_MISMATCH | High | 0 | 0 | 0
R15 | BENE_ACCOUNT_MISMATCH | Medium | 0 | 0 | 0
R16 | TRACE_ID_MISMATCH | High | 0 | 0 | 0
R17 | ROUTING_CHECKSUM_INVALID | High | 0 | 0 | 0
Total |  |  | 4010 | 0